## Overview
Key Dates:
|  |  |  | Launch PR, Website & Registration Live | 2015-06-26
|  |  |  | TrafficJam | 2/10/2015 - 4/10/2015
|  |  |  | Data & Ressources Live on Website | 2015-11-09
|  | JUNE |  |  |  |  | JULY |  |  |  | AUGUST |  |  |  |  | SEPTEMBER |  |  |  | OCTOBER
|  | 2015-06-01 | 2015-06-08 | 2015-06-15 | 2015-06-22 | 2015-06-29 | 2015-07-06 | 2015-07-13 | 20/7/2015 | 2015-07-27 | 2015-08-03 | 2015-08-10 | 2015-08-17 | 2015-08-24 | 2015-08-31 | 2015-09-07 | 2015-09-14 | 2015-09-21 | 2015-09-28 | 2015-10-05 | 2015-10-12 | 2015-10-19 | 2015-10-26
TrafficJam Milestones |  |  |  |  | LAUNCH June 26th |  |  |  |  | 2015-09-07: Resources & Data Links Live; 2015-09-28: TRAFFICJAM Oct. 2nd - 4th
Website
|  | Website and Registration Setup |  |  | Website + registration live
| News Section | [8 empty] | A | B | C | D |  | E & F | G | H | I | J | K | L
| Landing Page | [8 empty] | 2015-08-03: 1; 2015-08-10: 2; 2015-08-31: 3; 2015-09-07: 4; 2015-10-05: 5
Participant Engagement / Evaluation
| Engagement: Newsletter | [8 empty] | 2015-08-03: 2; 2015-08-17: 4; 2015-09-14: 6; 2015-09-28: 8; 2015-10-12: 9
| Evaluation & Confirmation: Registered Participants | [5 empty] | 1 |  |  | 2015-08-10: 3; 2015-08-24: 5; 2015-09-21: 7
Outbound Communication
| Press Releases (PR) & Media Advisories (MA) |  |  |  | A |  |  |  |  | 2015-08-24: B; 2015-08-31: C; 2015-09-28: D; 2015-10-05: E
| Recruitment: Hand Picked Participants | [8 empty] | 2015-08-17: Distribution of skill questionnaire & review & selection of participants
Social
| Facebook (1-2 posts per week) |  |  |  | facebook.com/TrafficJamTO: Proactive & Reactive Engagement (main goals: recruitment, Education using traffic stats, community building and during the hackathon: sharing the experience with a wider audience)
| Twitter (10-15 tweets per week) |  |  |  | @TrafficJamTO: Proactive & Reactive Engagement (main goals: recruitment, Education using traffic stats, community building and during the hackathon: sharing the experience with a wider audience)
| Reddit (as required) |  |  |  | Seeding Information |  |  |  |  | 2015-09-07: Seeding Information

## Communication
COMMUNICATION
PRs, MA's & Newsletters
| Week | # | Press Releases (PR) & Media Advisories (MA) | # | Newsletters / Email Outreach | Recipients
JUNE | 2015-06-22 | A | Launch Press Release
2015-06-29
JULY
| 2015-07-06 |  |  | 1 | Profiling Questionnaire | - Registered participants that hold tickets
2015-07-13
2015-07-20
2015-07-27
AUGUST
| 2015-08-03 |  |  | 2 | - Website News Update (A) - Website News Update (B) - Website Content Update (1) | - Registered participants that hold tickets - Participants registered on waitlist - Susbcribers from TrafficJam.to
| 2015-08-10 |  |  | 3 | Skill Focussed Questionnaire | - Participants registered on waitlist - Susbcribers from TrafficJam.to - Hackworks mailing lists
| 2015-08-17 |  |  | 4 | - Website News Update (C) - Website Content Update (2) - Website News Update (D) | - Registered participants that hold tickets - Participants registered on waitlist - Susbcribers from TrafficJam.to
| 2015-08-24 | B | Media Advisory for Press Conference | 5 | (AMA promotion) | - Registered participants that hold tickets - Participants registered on waitlist - Susbcribers from TrafficJam.to - Hackworks mailing lists - Hackworks Influencers to share with their network (depending on the are of focus: ODI Toronto, #DevTO, OneEleven, MaRS etc.)
| 2015-08-31 | C | Press Conference (or AMA), Press Release
SEPTEMBER
2015-09-07
| 2015-09-14 |  |  | 6 | - Website News Update (E & F) - Website Content Update (3) - Website News Update (G) - Website Content Update (4) - Website News Update (H) | - Registered participants that hold tickets - Participants registered on waitlist - Susbcribers from TrafficJam.to
| 2015-09-21 |  |  | 7 | Ticket Confirmation | - Registered participants that hold tickets
| 2015-09-28 | D | Media Advisory: TrafficJam Event | 8 | - Website News Update (I) - Website News Update (J) | - Registered participants that hold tickets - Participants registered on waitlist - Susbcribers from TrafficJam.to
OCTOBER
| 2015-10-05 | E | Winner Announcement Press Release |  |  | - Registered participants that hold tickets - Participants registered on waitlist - Susbcribers from TrafficJam.to
| 2015-10-12 |  |  | 9 | - Website News Update (K) - Website News Update (L) - Website Content Update (5) | - Registered participants that hold tickets - Participants registered on waitlist - Susbcribers from TrafficJam.to
2015-10-09
2015-10-26
Email Outreach
Newsletter Distribution

## Website
WEBSITE
Content Additions
| Week | # | News Section | Provided by | # | Landing Page | Provided by
JUNE | 2015-06-22
2015-06-29
JULY
2015-07-06
2015-07-13
2015-07-20
| 2015-07-27 | A | Sponsored Post: How data is being used in different countries to better traffic | Accenture
AUGUST
| 2015-08-03 | B | Blog Post: Details on Participant Briefing, Brainstorming & Teambuilding | Hackworks | 1 | Event schedule: Friday, Saturday, Sunday | Hackworks
| 2015-08-10 | C | Sponsored post: Gives insight on what drivers really care about and the cost of traffic congestion for the individual consumer. | CAA | 2 | Rules & Regulations | Hackworks
| 2015-08-17 | D | Sponsored Post: Outline of how data is currently collected and used to better traffic systems on highway | 407 ETR
2015-08-24
| 2015-08-31 | E | Blog Post: What we are looking for, scoping the event | Hackworks
|  | F | Press Release (AMA or press conference related) | Evergreen CityWorks | 3 | Judging & Prize: Judges, Criteria, Prizes | Hackworks
SEPTEMBER
| 2015-09-07 | G | Sponsored Post: Profile on vision for "open government" and why it's important (could modify Min. Matthews piece in Canada 2020 e-book) | Province of Ontario | 4 | Resources: - Data visualization tools - Links to all relevant data | Data visualization tools: City of Toronto Links to relevant data: City of Toronto, Province of Ontario, Sponsors & Partners
| 2015-09-14 | H | Sponsored Post: Overview of Google data tools and how open data, real time information and mapping can transform cities | Google
| 2015-09-21 | I | Sponsored Post: Profile on New Big Data Innovation team, their vision for how data can improve decision making and planning | City of Toronto
| 29/28/2015 | J | Blog Post: Explain how to best prepare for the Hackathon | Hackworks
OCTOBER | 2015-10-05 | K | Winner Announcement PR |  |  | Winner Profiles: 1st, 2nd, 3rd | Hackworks
| 2015-10-12 | L | Sponsored Post: Review of the first ever Hackathon at Evergreen Brick Works | Evergreen Brick Works
2015-10-09
2015-10-26
Legend:
Optional
Core
PR